## Sheet1
Software Phase | Processes | Roles | Man hrs,Days | Cost
Requirment Engg | Elicitation | Requirment Gathering | 10 days | 80000
| Use cases | Abstract view | 10 days | 20000
| Technology | Use for software Development eg sql server,asp.net | 20 days | 10000
| Non functional req | Increase the performance and security | 5days | 60000
Analysis and Design | High level Design | Make Activity and Sequence Diagram(Architectural view) | 30 Days | 50000
| Interface Design | Interface view | 15 Days | 50000
Code | LOC | Line of code count | 30 Days | 100000
Testing And Maintaince | Test case | Design Test Case for testing | 10 days | 40000
| Maintaince | Change in Furture (Architecture) | 20 days | 80000
Total |  |  |  | 490000